## Raw data
JPMC GFBM Virtual Experience Program
Task 1 - Data Analysis
Hypothetical Project Cost - Budget vs. Actual
[5 empty] | Budget Hours | [5 empty] | Actual Hours | [5 empty] | Budget Cost | [5 empty] | Actual Cost
| Project | Task | Resource | Cost $ / hr | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
| Project A | AT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 30 | 30 | 30 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500
| Project A | AT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 3150 | 3150 | 3150
| Project A | AT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
| Project A | AT1 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100
| Project A | AT1 | Jim | 90 | 140 | 140 | 140 | 140 | 140 | 140 | 160 | 160 | 160 | 160 | 160 | 160 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400
| Project A | AT2 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500
| Project A | AT2 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100
| Project A | AT3 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
| Project A | AT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project B | BT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
| Project B | BT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750
| Project B | BT1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project B | BT2 | Gail | 50 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
| Project B | BT2 | Monique | 105 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200
| Project B | BT2 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
| Project B | BT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project B | BT3 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project B | BT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
| Project C | CT1 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 500 | 500 | 500 | 500 | 500 | 500 | 250 | 250 | 250 | 250 | 250 | 250
| Project C | CT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800
| Project C | CT1 | Jenny | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
| Project C | CT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project C | CT2 | Monique | 105 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600
| Project C | CT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project C | CT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project C | CT3 | Gail | 50 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project C | CT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project C | CT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
| Project C | CT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project C | CT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project C | CT5 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
| Project C | CT5 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project D | DT1 | Jim | 90 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350
| Project D | DT1 | Inigo | 95 | 160 | 160 | 160 | 160 | 160 | 160 | 110 | 110 | 110 | 110 | 110 | 110 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 10450 | 10450 | 10450 | 10450 | 10450 | 10450
| Project D | DT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project D | DT1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project D | DT2 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
| Project D | DT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project D | DT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project D | DT2 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project D | DT3 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750
| Project D | DT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project D | DT3 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project D | DT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project D | DT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project D | DT4 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project E | ET1 | Gail | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
| Project E | ET1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project E | ET1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project E | ET2 | Sondra | 45 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200
| Project E | ET2 | Larry | 88 | 160 | 160 | 160 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 80 | 14080 | 14080 | 14080 | 14080 | 14080 | 14080 | 7040 | 7040 | 7040 | 7040 | 7040 | 7040
| Project E | ET2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project E | ET2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500

## Worksheet
|  |  |  | Budget Hours | [5 empty] | Actual Hours | [5 empty] | Budget Cost | [5 empty] | Actual Cost
Project | Task | Resource | Cost $ / hr | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Total Budgeted Hours | Total Actual Hours | Total Budgeted Cost | Total Actual Cost | Cost Variance | CPI | Estimated time | Projects | Month | Budgeted Hours | Actual Hours | Budgeted Cost | Actual Cost | Cost Variance
Project A | AT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 30 | 30 | 30 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 120 | 162 | 6000 | 8100 | -2100 | 1.35 | -42 | A | 1 | 360 | 386 | 25600 | 27700 | -2100
Project A | AT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 3150 | 3150 | 3150 | 480 | 510 | 16800 | 17850 | -1050 | 1.0625 | -30 | B | 1 | 225 | 268 | 21850 | 26100 | -4250
Project A | AT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240 | 240 | 18000 | 18000 | 0 | 1 | 0 | C | 1 | 460 | 538 | 36000 | 44050 | -8050
Project A | AT1 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 120 | 120 | 12600 | 12600 | 0 | 1 | 0 | D | 1 | 550 | 526 | 48500 | 45250 | 3250
Project A | AT1 | Jim | 90 | 140 | 140 | 140 | 140 | 140 | 140 | 160 | 160 | 160 | 160 | 160 | 160 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 840 | 960 | 75600 | 86400 | -10800 | 1.1429 | -120 | E | 1 | 430 | 369 | 29080 | 23040 | 6040
Project A | AT2 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 60 | 60 | 3000 | 3000 | 0 | 1 | 0 | A | 2 | 360 | 386 | 25600 | 27700 | -2100
Project A | AT2 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 120 | 120 | 12600 | 12600 | 0 | 1 | 0 | B | 2 | 225 | 268 | 21850 | 26100 | -4250
Project A | AT3 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 120 | 120 | 6000 | 6000 | 0 | 1 | 0 | C | 2 | 460 | 538 | 36000 | 44050 | -8050
Project A | AT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12 | D | 2 | 550 | 526 | 48500 | 45250 | 3250
Project B | BT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 120 | 144 | 6000 | 7200 | -1200 | 1.2 | -24 | E | 2 | 430 | 369 | 29080 | 23040 | 6040
Project B | BT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 240 | 300 | 18000 | 22500 | -4500 | 1.25 | -60 | A | 3 | 360 | 386 | 25600 | 27700 | -2100
Project B | BT1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12 | B | 3 | 225 | 268 | 21850 | 26100 | -4250
Project B | BT2 | Gail | 50 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 30 | 30 | 1500 | 1500 | 0 | 1 | 0 | C | 3 | 460 | 538 | 36000 | 44050 | -8050
Project B | BT2 | Monique | 105 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 240 | 240 | 25200 | 25200 | 0 | 1 | 0 | D | 3 | 550 | 526 | 48500 | 45250 | 3250
Project B | BT2 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 240 | 225 | 33600 | 31500 | 2100 | 0.9375 | 15 | E | 3 | 430 | 369 | 29080 | 23040 | 6040
Project B | BT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12 | A | 4 | 360 | 386 | 25600 | 28350 | -2750
Project B | BT3 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 120 | 150 | 7200 | 9000 | -1800 | 1.25 | -30 | B | 4 | 225 | 268 | 21850 | 19100 | 2750
Project B | BT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 240 | 225 | 33600 | 31500 | 2100 | 0.9375 | 15 | C | 4 | 460 | 538 | 36000 | 37050 | -1050
Project C | CT1 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 500 | 500 | 500 | 500 | 500 | 500 | 250 | 250 | 250 | 250 | 250 | 250 | 60 | 30 | 3000 | 1500 | 1500 | 0.5 | 30 | D | 4 | 550 | 526 | 48500 | 45250 | 3250
Project C | CT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 480 | 480 | 16800 | 16800 | 0 | 1 | 0 | E | 4 | 430 | 369 | 29080 | 23040 | 6040
Project C | CT1 | Jenny | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 480 | 480 | 36000 | 36000 | 0 | 1 | 0 | A | 5 | 360 | 386 | 25600 | 28350 | -2750
Project C | CT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 120 | 150 | 7200 | 9000 | -1800 | 1.25 | -30 | B | 5 | 225 | 268 | 21850 | 19100 | 2750
Project C | CT2 | Monique | 105 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 480 | 720 | 50400 | 75600 | -25200 | 1.5 | -240 | C | 5 | 460 | 538 | 36000 | 37050 | -1050
Project C | CT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12 | D | 5 | 550 | 526 | 48500 | 45250 | 3250
Project C | CT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 120 | 150 | 7200 | 9000 | -1800 | 1.25 | -30 | E | 5 | 430 | 369 | 29080 | 23040 | 6040
Project C | CT3 | Gail | 50 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 180 | 180 | 9000 | 9000 | 0 | 1 | 0 | A | 6 | 360 | 386 | 25600 | 28350 | -2750
Project C | CT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12 | B | 6 | 225 | 268 | 21850 | 19100 | 2750
Project C | CT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 240 | 225 | 33600 | 31500 | 2100 | 0.9375 | 15 | C | 6 | 460 | 538 | 36000 | 37050 | -1050
Project C | CT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12 | D | 6 | 550 | 526 | 48500 | 45250 | 3250
Project C | CT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 120 | 150 | 7200 | 9000 | -1800 | 1.25 | -30 | E | 6 | 430 | 369 | 29080 | 23040 | 6040
Project C | CT5 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 240 | 225 | 33600 | 31500 | 2100 | 0.9375 | 15
Project C | CT5 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12
Project D | DT1 | Jim | 90 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 120 | 90 | 10800 | 8100 | 2700 | 0.75 | 30
Project D | DT1 | Inigo | 95 | 160 | 160 | 160 | 160 | 160 | 160 | 110 | 110 | 110 | 110 | 110 | 110 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 10450 | 10450 | 10450 | 10450 | 10450 | 10450 | 960 | 660 | 91200 | 62700 | 28500 | 0.6875 | 300
Project D | DT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 120 | 150 | 7200 | 9000 | -1800 | 1.25 | -30
Project D | DT1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 180 | 180 | 21600 | 21600 | 0 | 1 | 0
Project D | DT2 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 480 | 480 | 36000 | 36000 | 0 | 1 | 0
Project D | DT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12
Project D | DT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 120 | 150 | 7200 | 9000 | -1800 | 1.25 | -30
Project D | DT2 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 180 | 180 | 21600 | 21600 | 0 | 1 | 0
Project D | DT3 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 480 | 540 | 36000 | 40500 | -4500 | 1.125 | -60
Project D | DT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12
Project D | DT3 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 180 | 180 | 21600 | 21600 | 0 | 1 | 0
Project D | DT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12
Project D | DT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 120 | 150 | 7200 | 9000 | -1800 | 1.25 | -30
Project D | DT4 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 180 | 180 | 21600 | 21600 | 0 | 1 | 0
Project E | ET1 | Gail | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 240 | 300 | 12000 | 15000 | -3000 | 1.25 | -60
Project E | ET1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12
Project E | ET1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 180 | 180 | 21600 | 21600 | 0 | 1 | 0
Project E | ET2 | Sondra | 45 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 960 | 960 | 43200 | 43200 | 0 | 1 | 0
Project E | ET2 | Larry | 88 | 160 | 160 | 160 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 80 | 14080 | 14080 | 14080 | 14080 | 14080 | 14080 | 7040 | 7040 | 7040 | 7040 | 7040 | 7040 | 960 | 480 | 84480 | 42240 | 42240 | 0.5 | 480
Project E | ET2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 60 | 72 | 3000 | 3600 | -600 | 1.2 | -12
Project E | ET2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 120 | 150 | 7200 | 9000 | -1800 | 1.25 | -30
|  |  |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2087 | 2087 | 2087 | 2003 | 2003 | 2003 | 161030 | 161030 | 161030 | 161030 | 161030 | 161030 | 166140 | 166140 | 166140 | 152790 | 152790 | 152790 | 12150 | 12270 | 966180 | 956790 | 9390
| Project A |  |  | 360 | 360 | 360 | 360 | 360 | 360 | 386 | 386 | 386 | 402 | 402 | 402 | 25600 | 25600 | 25600 | 25600 | 25600 | 25600 | 27700 | 27700 | 27700 | 28350 | 28350 | 28350 | 2160 | 2364 | 153600 | 168150 | -14550
| Projet B |  |  | 225 | 225 | 225 | 225 | 225 | 225 | 268 | 268 | 268 | 218 | 218 | 218 | 21850 | 21850 | 21850 | 21850 | 21850 | 21850 | 26100 | 26100 | 26100 | 19100 | 19100 | 19100 | 1350 | 1458 | 131100 | 135600 | -4500
| Project C |  |  | 460 | 460 | 460 | 460 | 460 | 460 | 538 | 538 | 538 | 488 | 488 | 488 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 44050 | 44050 | 44050 | 37050 | 37050 | 37050 | 2760 | 3078 | 216000 | 243300 | -27300
| Project D |  |  | 550 | 550 | 550 | 550 | 550 | 550 | 526 | 526 | 526 | 526 | 526 | 526 | 48500 | 48500 | 48500 | 48500 | 48500 | 48500 | 45250 | 45250 | 45250 | 45250 | 45250 | 45250 | 3300 | 3156 | 291000 | 271500 | 19500
| Project E |  |  | 430 | 430 | 430 | 430 | 430 | 430 | 369 | 369 | 369 | 369 | 369 | 369 | 29080 | 29080 | 29080 | 29080 | 29080 | 29080 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 2580 | 2214 | 174480 | 138240 | 36240

## Pivot Table
Row Labels | Total Budget Costs | Total Actual Costs | Sum of Cost Variance
Project A | 153600 | 168150 | -14550
Project B | 131100 | 135600 | -4500
Project C | 216000 | 243300 | -27300
Project D | 291000 | 271500 | 19500
Project E | 174480 | 138240 | 36240
Grand Total | 966180 | 956790 | 9390
Sum of Total Actual Cost | Column Labels
Row Labels | Project A | Project B | Project C | Project D | Project E | Grand Total
Monique | 25200 | 25200 | 75600 |  |  | 126000
Erica |  | 63000 | 63000 |  |  | 126000
Crystal |  |  |  | 86400 | 21600 | 108000
Jim | 86400 |  |  | 8100 |  | 94500
Jenny | 18000 | 22500 | 36000 |  |  | 76500
Sarah |  |  |  | 76500 |  | 76500
George |  | 9000 | 27000 | 27000 | 9000 | 72000
Inigo |  |  |  | 62700 |  | 62700
Gail | 17100 | 8700 | 10500 |  | 15000 | 51300
Stanley | 3600 | 7200 | 14400 | 10800 | 7200 | 43200
Sondra |  |  |  |  | 43200 | 43200
Larry |  |  |  |  | 42240 | 42240
Tom | 17850 |  | 16800 |  |  | 34650
Grand Total | 168150 | 135600 | 243300 | 271500 | 138240 | 956790
| Avg of Total Budgeted Hours | Avg of Total Actual Hours
Stanley | 60 | 72
Gail | 116.25 | 128.25
George | 120 | 150
Crystal | 180 | 180
Erica | 240 | 225
Monique | 240 | 300
Jenny | 320 | 340
Jim | 480 | 525
Tom | 480 | 495
Sarah | 480 | 510
Sondra | 960 | 960
Larry | 960 | 480
Inigo | 960 | 660
Grand Total | 229.2453 | 231.5094

## Pivot Table 2
Row Labels | Sum of Budgeted Hours | Sum ofActual Hours
Project A | 2160 | 2364
Project B | 1350 | 1458
Project C | 2760 | 3078
Project D | 3300 | 3156
Project E | 2580 | 2214
Grand Total | 12150 | 12270
Sum of Total Actual Hours | Column Labels
Row Labels | Crystal | Erica | Gail | George | Inigo | Jenny | Jim | Larry | Monique | Sarah | Sondra | Stanley | Tom | Grand Total
Project A |  |  | 342 |  |  | 240 | 960 |  | 240 |  |  | 72 | 510 | 2364
Project B |  | 450 | 174 | 150 |  | 300 |  |  | 240 |  |  | 144 |  | 1458
Project C |  | 450 | 210 | 450 |  | 480 |  |  | 720 |  |  | 288 | 480 | 3078
Project D | 720 |  |  | 450 | 660 |  | 90 |  |  | 1020 |  | 216 |  | 3156
Project E | 180 |  | 300 | 150 |  |  |  | 480 |  |  | 960 | 144 |  | 2214
Grand Total | 900 | 900 | 1026 | 1200 | 660 | 1020 | 1050 | 480 | 1200 | 1020 | 960 | 864 | 990 | 12270
Row Labels | Avg of Time accuracy
Project A | -22.6667
Project B | -12
Project C | -22.7143
Project D | 10.2857
Project E | 52.2857
Grand Total | -2.2642

## Pivot Table 3
Sum of Budgeted Cost | Column Labels
Row Labels | 1 | 2 | 3 | 4 | 5 | 6 | Grand Total
A | 25600 | 25600 | 25600 | 25600 | 25600 | 25600 | 153600
B | 21850 | 21850 | 21850 | 21850 | 21850 | 21850 | 131100
C | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 216000
D | 48500 | 48500 | 48500 | 48500 | 48500 | 48500 | 291000
E | 29080 | 29080 | 29080 | 29080 | 29080 | 29080 | 174480
Grand Total | 161030 | 161030 | 161030 | 161030 | 161030 | 161030 | 966180
Sum of Actual Cost | Column Labels
Row Labels | 1 | 2 | 3 | 4 | 5 | 6 | Grand Total
A | 27700 | 27700 | 27700 | 28350 | 28350 | 28350 | 168150
B | 26100 | 26100 | 26100 | 19100 | 19100 | 19100 | 135600
C | 44050 | 44050 | 44050 | 37050 | 37050 | 37050 | 243300
D | 45250 | 45250 | 45250 | 45250 | 45250 | 45250 | 271500
E | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 138240
Grand Total | 166140 | 166140 | 166140 | 152790 | 152790 | 152790 | 956790
Sum of Cost Variance | Column Labels
Row Labels | 1 | 2 | 3 | 4 | 5 | 6 | Grand Total
A | -2100 | -2100 | -2100 | -2750 | -2750 | -2750 | -14550
B | -4250 | -4250 | -4250 | 2750 | 2750 | 2750 | -4500
C | -8050 | -8050 | -8050 | -1050 | -1050 | -1050 | -27300
D | 3250 | 3250 | 3250 | 3250 | 3250 | 3250 | 19500
E | 6040 | 6040 | 6040 | 6040 | 6040 | 6040 | 36240
Grand Total | -5110 | -5110 | -5110 | 8240 | 8240 | 8240 | 9390

## Dashboard
Project Cost - Budget to Actual Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.